## Team_3
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2024-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A person joins the team | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Quickly onboard new member | Does not apply as of now | Open
| Lack of motivation or responsibility | Team members lack motivation to complete tasks | 3 | 3 | 3 | 27 | Team leader and all members | 2024-06-01 | Have regular weekly check-ins and 1-on-1's if needed | Ongoing communication and check-ins | Open
Communication | duplicate work | Team members are duplicating work | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Use project management tools like GitHub KanBan or something else to avoid duplications along with regular meetings | No duplicated work detected | Open
| worked on wrong components | Team member worked on wrong component | 1 | 3 | 2 | 20 | Team leader | 2024-06-01 | Regular check-ins and meetings along with a project management tool to prevent that | No wrong work detected | Open
| useless work | Work done that isn't useful to the project | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review work in meetings to check for work relevance | Hasn't happened | Open
| inconsistent work | Work quality is inconsistent | 2 | 3 | 2 | 24 | Tem leader and all members | 2024-06-01 | Follow coding standards and guidelines to review work consistency | Ongoing | Open
Requirements | unclear requirements | Requirements are not clearly defined | 2 | 4 | 3 | 36 | Requirement Leader | 2024-06-01 | Regular meetings with stakeholders to clarify and refine requirements. | Ongoing requirement refinement | Open
| scope creep | Uncontrolled changes in project scope | 3 | 4 | 3 | 27 | Team leader | 2024-06-01 | Implement change control process to manage scope changes. | Scope changes under control | Open
| constant requirements changes | Frequent changes in requirements | 3 | 4 | 3 | 27 | Requirement Leader | 2024-06-01 | Regular communication with stakeholders and iterative development to manage changes. | Managed through iterative updates | Open
Management | improper task assignments | Tasks not assigned properly | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review and adjust task assignments based on team skills and project needs. | Tasks reviewed regularly | Open
| improper planning | Poor planning of project phases | 2 | 4 | 3 | 36 | Team leader | 2024-06-01 | Regular planning sessions and reviews to ensure proper project planning. | Planning sessions ongoing | Open
| lack of management skills | Team lacks management skills | 2 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide management training and support for the team leader. | Ongoing management training | Open
Technology competence | Not familiar with the framework used | Team not familiar with Django framework | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Django. | Training sessions scheduled | Open
| Not familiar with the programming language used | Team not familiar with Python | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Python. | Training sessions scheduled | Open
| Not familiar with unit testing | Team not familiar with unit testing | 3 | 3 | 3 | 27 | QA Leader | 2024-06-01 | Provide training on unit testing practices and tools. | Training sessions scheduled | Open
| Other technology incompetence | Team lacks other necessary technology skills | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Identify skill gaps and provide training and resources. | Ongoing skills assessment | Open
| Not familiar with Git | Team not familiar with Git for version control | 3 | 3 | 3 | 27 | Configuration Leader | 2024-06-01 | Provide Git training and best practices documentation. | Training sessions scheduled | Open
Design and implementation | Improper design | Design does not meet project requirements | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Regular design reviews and stakeholder feedback sessions. | Design reviews ongoing | Open
| improper technology stack | Technology stack not suitable for project | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Evaluate and select technology stack based on project needs and team expertise. | Technology stack evaluated | Open
| Messy code | Code is disorganized and difficult to maintain | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-06-01 | Establish and enforce coding standards and conduct regular code reviews. | Coding standards enforced | Open
Testing | Not enough testing | Insufficient test coverage | 3 | 4 | 3 | 36 | QA Leader | 2024-06-01 | Ensure comprehensive test coverage by setting up testing frameworks and writing necessary tests. | Testing in progress | Open
Integration and deployment | Not enough time for integration and deployment | Inadequate time allocated for integration and deployment | 3 | 4 | 4 | 48 | Team leader and Configuration Leader | 2024-06-01 | Allocate sufficient time for integration and deployment phases in the project plan. | Time allocated in project plan | Open