## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/07 - 05/15 | Created initial plan |  | Some other members are joining the team late | Create more communication points | 0 | 0 | 0 | 0 | 0 | 49.5 | 44.5 | 5 | 14 | 4 | 0 | 1.5 | 0 | 15 | 6
1 | 05/16 - 05/28 | Switched to different project idea | There were some issues of setting up Django env and tests | A member of our team has left | Have more meetings and open communication | 6 | 11 | 0 | 0 | 0 | 118 | 117 | 1 | 10 | 32.5 | 10 | 37 | 13.5 | 12 | 2
2 | 05/28 - 06/11 | Finalizing Django models for Iteration3 where DB will be implemented and deleted a lot of useless code | Learning which code to keep and remove was difficult at first | We're on a tighter schedule for this and the next iteration making it hard to implement new things |  | 8 | 6 | 0 | 2 | 6 | 154 | 141.5 | 12.5 | 12.5 | 3 | 6 | 52 | 13.5 | 15.5 | 22
3 | 06/11 - 06/18 | Project was finalized | There was an issue with user facilitator tests not working as expected but was fixed | The biggest issue was only one week to fix the previous iteration issues and ship whatever remaining features we had |  | 17 | 0 | 9 | 9 | 0 | 86 | 80 | 6 | 8 | 3.5 | 20 | 8.5 | 15 | 20 | 7

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Adrian Ortiz
Magnus Urosev | Created draft and first full version of SPPP along with all documents needed for Iteration0. Updated SPPP through every iteration and submitted Edited document and prepared for submission of Iteration1 Edited and prepared document for submission of Iteration2 | Over saw and assigned some user stories on pivotal tracker | Created initital SDD for submission of Iteration0 and applied later feedback from Iteration0 for submission of Iteration1 also for Iteration2 and Iteration3. Add missing software architecture diagram and class diagram on ORM. | Created initial draft for Iteration1 and refined for Iteration2 and finalized for Iteration3. | Prepared and presented presentations for Iteration 0 and Iteration 1 and created and organized PowerPoint for the final presentation. Assigned roles and speaking points to each member for final presentation. | Added intial backend code for Django and reviewed and approved Pull Requests | Created unittests for submission of Iteration1 testing the implementation of question and survey models. 23 tests made within the Django test, 100% pass. |  | Lead and organized team through iterations using discord and hosted almost all meetings and one on ones when needed Facilitated meeting via zoom Reached out privately with group memebers and facilitated 1-on-1s to make sure everyone was on track
Jack Cairns | Researched and documented sililar products to ours | Tracked status of stories on pivotal tracker |  | Discussed testing and automation in the document | Demo of automation and design | Implemented core Django Models and API Serializers, kept the code base in a working state. I managed PR's and monitored changes coming into the code base. |  |  | Regular meeting minutes taker
Xi Zeng |  |  | Updating all ERD for DB | Updateing the newer version of automated testing | Demo the app for the last iteration | Implemented survey platform for users take and view surveys, group api for surveys | Implemented selenium and API automated testing; Factored previous automated testing; Revised bugs by manually testing | Wrote readme for surveys folder and users folder for testing

## AdrianOrtiz
Your Lead Roles: Configuration Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 10 | 9 | 1 | 0 - learn django, read several tutorials, look into various DevOps tools for project, assess pros/cons 1 - define high level requirements and coding standards, and tools needed for project, research similar products and figure out which to commit to 3 - Implemet Source Control, Coding standards, IDE, and misc DevOps tools, implement teammate feedback (when applicable) 5 - Inform teammates on decision of Tools, get feedback from teammates, create documentation when applicable, provide documentation and relevant links 6 - set up git, setup planning board, organize google drive folder, commit to tools for project, create environments doc | 3 | 1 | 0 | 1.5 | 0 | 0.5 | 3 | 0 | Defined high level requirements and coding standards, and tools needed for project, research similar products and figure out which to commit to Informed teammates on decision of Tools, created documentation when applicable, provided documentation and relevant links. Set up git, setup planning board, organize google drive folder, commit to tools for project, create environments doc. | CI/CD implementation giving issues using AWS | Will try to switch to docker for simplicity | Fix CI/CD code, implement code for assigned tasks (TBD) | 40
2 | 05/16 - 05/28 | 43 | 43 | 0 | 1 - Understand the requirements for implementing my 2 User Stories: User Registration and User Login 2 - Design both user stories 3 - Write the code for both user stories 4 - Test my code on a custom feature branch before making a merge request 5 - Update team of my availability and communicate over discord and get caught up on what I missed 6 - create some frontend code for implementing user stories | 0 | 0.5 | 2 | 30 | 10 | 0.5 | 10 (out of the 30 hours indicated on 3) | 0 | Designed 2 User Stories: User Registration and User Login. Applied the requirements for implementing my 2 User Stories. Write frontend and backend code for both user stories. Tested my code on a custom feature branch before making a merge request. Updated the team of my availability and communicated over discord how I could get caught up on what I missed and then caught up on it. | Needed to create a seperate folder to isolate my code and get it to run properly... | Code works, just need to implement it to the further stack... | - Whatever my assigned tasks are - Integrate code with code base and clean up files - Implement DB writing to save user input | 40
3 | 05/28 - 06/11 | 81.5 | 80 | 1.5 | 0 - Learned how to do the tasks that were required for my code changes 2 - Design home page for user login / registration && Ensure DB Persistance of data, specify criteria for registration (password requirements), make warnings accordingly for issues found upon creation / login. 3 - Write the code for implementing home page, password checks, proper error messages, and DB Persistance 4 - Test both hyperlinks on the home page (Registration & User login), Test Registration flow including error messages, test user login flow, ensure students can not login to the admin portal, ensure only instructors/admins can login to the admin portal, verify DB persistance 5 - Update team of my progress, Ran 1 team meeting, created instructions on how to run my code locally and placed in github for teammates to view, worked with team to make it to the other meetings 6 - created some frontend code for implementing home page, moved away from github actions for ci/cd in order to move towards docker for automation testing, succesfully setup docker container to run code / test, Made a PR of working changes to integrate code into main 7 - I was the presenter this week so I created a powerpoint presentation and recorded a video presenting it and demoed the code and also did some video editing to trim out the unecessary part in order to keep the video relatively short. | 2 | 0 | 5 | 40 | 10 | 3 | 10 | 10 | Designed home page for user login / registration && Ensured DB Persistance of data. Created specific criteria for registration such as password requirements and made warnings accordingly for issues found upon registration and login. Wrote the code for implementing home page, password checks, proper error messages, and DB Persistance.Tested both hyperlinks on the home page (Registration & User login), Tested the registration flow including error messages, test user login flow. Ensured that students could not login to the admin portal and only instructors/admins could login. I also verified DB persistance of created users and deleted users.I updated the team of my progress, I ran 1 team meeting, created instructions on how to run my code locally and placed them in github for teammates to view, and I worked with the team to make it to the other meetings. Lastly I decided to move away from github actions for ci/cd in order to move towards docker for automation testing and succesfully setup a docker container to run and test my code. Once it passed, I created a PR of the working changes so that they could integrate the code into main. I was also the presenter this week so I created a powerpoint presentation and recorded a video presenting it and demoing the code and also did some video editing to trim out the unecessary part in order to keep the video relatively short. | - Could not get github actions to work properly so needed to ax it entirely - Had issues with running docker through my local terminal since it was not set to a virtual env | - Move to docker for automation testing - Figure out why the code doesn't work properly outside a venv - Learn how to create automation testing in docker 😅 | - Automation testing both learning how to write it and implement it - Make code idempotent and OS agnostic | 30
4 | 06/11 - 06/18 | 8.5 | 5.5 | 3 | 4 - Tested new changes made by teammates, tested new changes made to DB such as changing from sqllite to postgres 5 - Kept team updated on my availability and when it would be best to have meetings so that I would be able to attend, reached out for help when I was blocked and asked for assistance 6 - Further refined Github Project Repo and updated the README file accordingly 7 - Created the Security Requirements Powerpoint slide for the Final presentation and presented it as well for the presentation recording | 0 | 0 | 0 | 0 | 2 | 0.5 | 2 | 1 | I tested the new changes made by my teammates and tested the new changes I made to the DB such as changing from sqllite to postgres. I also kept the team updated on my availability and when it would be best to have meetings so that I would be able to attend, I also reached out for help when I was blocked and asked for assistance. I further refined the Github Project Repo and updated the README file accordingly. I also created the "Security Requirements" power point slide for the final presentation and presented it as well for the presentation recording. | I had lots of issues with testing, primarily because I am on a mac and the tests were written for Windows. | No real issue, I can potentially setup a Windows VM or a GH runner and run the code there to see it compiled. | N/A | 0
Your Lead Roles: Configuration Leader, Security Leader

## MagnusUrosev
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 22 | 20 | 2 | 0 - Reviewed Git documentation along with Django, Pandas, and NumPy 1 - Defined high level requirements and distributed roles to team 5 - Managed with team3 and other teams on our project and plan. Filled in team members that joined a bit later due to Spring semseter finals. 7 - Researched scholarly articles on psychometric and exam modeling and how to implement that on the backend without needing to import too many new packages | 3 | 2 |  |  |  | 11 |  | 4 | 1. Wrote SPPP, Risk, Progress report and other documents for iteration 1 2. Created github and led team through lab1 3. Organized and led meetings to present project 4. Looped in teammates that had joined the team late | 1. Communication with other teams is unclear and unsure of their services 2. Some teammates are unfamiliar with Pandas, NumPy, Django, and Git | 1. Continue to promote open communication with other teams and invent team leaders/representatives to sit in on our meetings. I will offer to sit in on their meetings as well to understand their current project visions 2. Continue to provide resources and assisstance when needed to make sure all team memebers are comfortable with said libraries and frameworks | 2 - Design a data model for calculating statistics and processing information to FE team 3 - Implement statistics model | 25
2 | 05/16 - 05/28 | 56 | 56 |  | 2 - Created the base Django and Front End code for the project which others developed on 3 - Implemented base models and survey model for Django 4 - Created tests for the Survey and question implementation 5 - Scheduled meetings and delegated tasks to team members and reached out to check progress 7 - Completing needed documents for iteration 1 |  | 30 | 8 | 3 | 2 | 10 |  | 3 | 2 - Created the base code in code as seen in commits 3 - Created base model placeholders as seen in commits 4 - Seen in my personal branch 5 - Seen through minutes and discord messages 7 Submission of iteration 1 | 1 - Not everyone is on the same page with development 2 - A member has left the team | 1 - Schedule more frequent meetings and check-ins 2 - Divide tasks amongst teammates | 1 - Create Data base 2 - Configure env for data base and testing | 60
3 | 05/16 - 05/28 | 42 | 32 | 10 | 0 - Reviewed Django documentation and OO design patterns 5 - Facilitated group discussion via zoom and discord 6 - Had issues with personal docker env and had to fix | 10 |  |  |  |  | 10 | 12 |  | 5 - Assignment of group tasks via discord and meeting notes | 0 - Poor choice of OO design of composite for question and survey model. Switched to factory. | 1 - Revised pattern and updated in SDD | 1 - Revise user login 2 - Assign presentation of Iteration2 to another teammate | 120
4 | 05/28 - 06/11 | 40 | 40 |  | 2 - Revised PR requests on GitHub over code refactoring and different implementations 4 - Testing PR before merging 5 - Facilitating communications and administering tasks to other teammates and teams 6 - Had personal laptop issues and had to rebuild venv |  |  | 10 |  | 10 | 15 | 5 |  | 2 - Merges on GitHub 4 - Merged PR on GitHub 5 - Assignment and updates via meetings. Team1 reached out to me regarding some Auth email service | 1 - Two people still need to present for one of the Iterations 2 - Had to delay DB implementation to Iteration3 | 1 - Jack and Xi will present for Iteration3 2 - Xi will implement and present DB | 1 - Implement and test DB 2 - Prepare for final push | 160
5 | 06/11 - 06/18 | 33 | 33 |  | 2 - Completing UML diagrams for presentation and documentation 4 - Testing pull requests before merging onto main 5 - Hosting meetings and communicating with team members via discord or privately on tasks 7 - Reviewing feedback on documents from previous iterations |  |  | 10 |  | 5 | 10 | 8 |  | 4 - Merged team members pull requests onto main 5 - Team members are completing assigned tasks 7 - Made changes to documents | 1. Tight deadline 2. Scheduling issues | 1. Do whatever is needed to deliver the mininum viable product 2. Send more reminders on tasks and deadlines | 0 - The class will be over | NA

## JackCairns
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 9.5 | 8.5 | 1 | 0 - review GitHub and its features, read through class documents about the project, read throug team coding standards 5 - minutes for first team meeting, informal meeting with team to ask questions to team leader 6 - set up GitHub access to repository key, joined team3, and debugged contributor errors | 3 |  |  |  |  | 2.5 | 3 | 0 |  | 1. I had an issue with GitHub not showing me as a contributor to my team's project 2. I had a late start to the course due to Spring courses | 1. Needed to add my BU email address to my GitHib account and have that match the email set in my local git config 2. Increase my time committmet and overall contributions in interations going forward | 0 - learn & review Django, Pandas, and NumPy, learn about my role as requirment leader 1 - review team design and provide concrete requirements based on other teams' plans 3 - implement a basic hello world on Django 5 - participate more in team activities 6 - setup PyCharm and Docker for local development environment | 6
2 | 05/16 - 05/28 | 13 | 13 |  | 0 - reviewing django class documentation 1 - writing and grooming stories 3 - implementation for question, choice, and response models 4 - Manual testing of APIs to access models 5 - minutes for meeting on 5/20 6 - spent time setting up Django virtualized docker envirionment for consistency in test and to best conform to the deployment environment | 2 | 2 |  | 4 | 1.5 | 1.5 | 2 |  | I write user stories to capture the work required to create the core models of the project. Implemented core models for the proiject and their trelationships with one another, tested GET and POST HTTP requests for each model against a sqlite database. | 2,3 - I struggled with the structure of the code at first, but I think I understand where to develop my code contributions now | 5 - I reached out to the team via discord on Saturday, 5/25. Magnus was able to provide me with the contesxt that I was missing to continue to work and make progress. | 4 - Fully automate testing with pytrhon unittest for Django. Have unit test repotrs generate as part of the automation | 15
4 | 05/28 - 06/11 | 22.5 | 22.5 |  | 0 - reviewing django project documentation needed to debug code issues 1 - created stories for the team for the final iteration 3 - integrated several features into the team's working project. I got the code building and running again 4 - tested features developed by the team to understand how best to integrate them 5 - attended all team meetings and regularly take down minutes | 2.5 | 2 |  | 12 | 3.5 | 2.5 |  |  | Integrated all features developed by all members of the team into a working, concise Django project. Removed several lines of duplicate code and other smells in the process. Updated README with instructions for others to run our code. | I had several issues tracking how some of the code made it into the repository. I duscussed with the team the importance of code reviews and GitHub's PR process | The team listened to my concerns and will be mindful of code commits going forward | Support development of unit tests and deployment automation with Docker | 25
5 | 06/11 - 06/18 | 13.5 | 13.5 |  | 1 - Updated and tracked user story progress on pivotal tracker 3 - Implemented Dockerfiles for deploying and testing the app. Updated README with instructions on how to run and test our code 4 - Implemented automated testing of model unit tests within the code base using Docker 5 - Document contribution and addressing feedback in SPPP and STD | 0 | 1.5 |  | 5.5 | 3 | 3.5 |  |  | Coordinated with team members to implement automation surrounding their code contributions. Maintained executable code within the code base and delivered demonstrations of testing automation in the final presentation | I did not have many issues this iteration. I think this team was just getting started working as a team with high velocity.

## XiZeng
Your Lead Roles: QA Leader / Design and Implementation Leader (DBs)
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 8 | 7 | 1 | 0 - learning git for team collaborate enviroment, django framework, revewing DBs, also learning from our course module 1 1 - Deside to use pandaSQL and django's build-in testing 5 - Understanding our specific micro-service needs from ZOOM Q&A, communicate in first team meeting | 5 | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  | Not farmiliar with pandaSQL, django's build-in testing, and git for team collaborate enviroment | Learning pandaSQL, django's build-in testing, and git for team collaborate enviroment from online enviroment | Building first draft ERD for DBs, Thinking throgh testing case from DBs side and communicating with teamate for their aspect of testing case. | 10
2 | 05/16 - 05/28 | 5 | 5 | 0 | 0 - Learning matirial from course and finish the quiz | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | I went back China and needed VPN to get connected to discord and google's enviroment | Review the meetings and catch up the progress | Building first draft ERD for DBs, Thinking throgh testing case from DBs side and communicating with teamate for their aspect of testing case. | 20
3 | 05/16 - 05/28 | 7 | 7 | 0 | 0 - Learning matirial from course 1 - analysing what we need for the DB to design a ERD 2 - starting design a ERD for DB | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Changing the Ideal of exam to survey | Revise the design | Finish the ERD and start the DB design | 40
4 | 05/28 - 06/11 | 23 | 21 | 2 | 0 - Learning matirial from course and finish the quiz 1 - based on updates to analysis the DB needs 2 - finished the ERD and DB design 3 - implement the Model and admin for DB | 5 | 2 | 10 | 3 | 0 | 1 | 0 | 0 | ERD for DB, Models and admin for DB | Finding that we don't have much time to do, so the ERD would be ideal model. | Focusing on finishing the suvey DB in a more sample way, the ERD would be the complete model. | Finishing the survey model and finish auto testing for survey model | 60
5 | 06/11 - 06/18 | 57 | 54 | 3 | 0 - Learning matirial from course and finish the quiz 2 - Design a survey platform that users can take surveys and view their survey results 3 - Implement the survey webserver for survey, and automated testing for functionality, quality, accuracy 4 - Manually and automated testing to find bugs in the code, then revised bugs 5 - Group meetings and showing the code functionalities 6 - Writing readme.md for users and surveys folder to illustrate the functionalities and how to testing by Django | 5 | 0 | 6 | 30 | 10 | 2 | 1 | 0 | Survey platform, group up survey api, simplify previous testing, design and implement api testing, selenium automated testing | Doesn't have enough time to fine-tune the webserver and revise the api of falcuty side that requires login to protect the survey takers. | Found of the improtance of risk management, as I was lost of connect with teammate. | End of class | 0