## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/07 - 05/15
1 | 05/16 - 05/28 |  | There were some issues of setting up Django env and tests | A member of our team has left | Have more meetings and open communication | 6 | 11 | 0 | 0 | 0 | 110 | 50 | 5 | 3 | 7 | 5 | 10 | 10 | 10 | 10
2 | 05/28 - 06/11
3 | 06/11 - 06/18

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Adrian Ortiz
Magnus Urosev | Created draft and first full version of SPPP along with all documents needed for Iteration0 |  |  |  |  | Added intial backend code for Django |  |  | Lead and organized team through iterations
Jack Cairns
Jianing Li
Xi Zeng

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## AdrianOrtiz
Your Lead Roles: Configuration Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 10 | 9 | 1 | 0 - learn django, read several tutorials, look into various DevOps tools for project, assess pros/cons 1 - define high level requirements and coding standards, and tools needed for project, research similar products and figure out which to commit to 3 - Implemet Source Control, Coding standards, IDE, and misc DevOps tools, implement teammate feedback (when applicable) 5 - Inform teammates on decision of Tools, get feedback from teammates, create documentation when applicable, provide documentation and relevant links 6 - set up git, setup planning board, organize google drive folder, commit to tools for project, create environments doc | 3 | 1 | 0 | 1.5 | 0 | 0.5 | 3 | 0 | Defined high level requirements and coding standards, and tools needed for project, research similar products and figure out which to commit to Informed teammates on decision of Tools, created documentation when applicable, provided documentation and relevant links. Set up git, setup planning board, organize google drive folder, commit to tools for project, create environments doc. | CI/CD implementation giving issues using AWS | Will try to switch to docker for simplicity | Fix CI/CD code, implement code for assigned tasks (TBD) | 40
2 | 05/16 - 05/28 | 43 | 43 | 0 | 1 - Understand the requirements for implementing my 2 User Stories: User Registration and User Login 2 - Design both user stories 3 - Write the code for both user stories 4 - Test my code on a custom feature branch before making a merge request 5 - Update team of my availability and communicate over discord and get caught up on what I missed 6 - create some frontend code for implementing user stories | 0 | 0.5 | 2 | 30 | 10 | 0.5 | 10 (out of the 30 hours indicated on 3) | 0 | Designed 2 User Stories: User Registration and User Login. Applied the requirements for implementing my 2 User Stories. Write frontend and backend code for both user stories. Tested my code on a custom feature branch before making a merge request. Updated the team of my availability and communicated over discord how I could get caught up on what I missed and then caught up on it. | Needed to create a seperate folder to isolate my code and get it to run properly... | Code works, just need to implement it to the further stack... | - Whatever my assigned tasks are - Integrate code with code base and clean up files - Implement DB writing to save user input | 40
3 | 05/16 - 05/28 | 0 | 0
4 | 05/28 - 06/11 | 0 | 0
5 | 06/11 - 06/18 | 0 | 0

## Magnus Urosev
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 22 | 20 | 2 | 0 - Reviewed Git documentation along with Django, Pandas, and NumPy 1 - Defined high level requirements and distributed roles to team 5 - Managed with team3 and other teams on our project and plan. Filled in team members that joined a bit later due to Spring semseter finals. 7 - Researched scholarly articles on psychometric and exam modeling and how to implement that on the backend without needing to import too many new packages | 3 | 2 |  |  |  | 11 |  | 4 | 1. Wrote SPPP, Risk, Progress report and other documents for iteration 1 2. Created github and led team through lab1 3. Organized and led meetings to present project 4. Looped in teammates that had joined the team late | 1. Communication with other teams is unclear and unsure of their services 2. Some teammates are unfamiliar with Pandas, NumPy, Django, and Git | 1. Continue to promote open communication with other teams and invent team leaders/representatives to sit in on our meetings. I will offer to sit in on their meetings as well to understand their current project visions 2. Continue to provide resources and assisstance when needed to make sure all team memebers are comfortable with said libraries and frameworks | 2 - Design a data model for calculating statistics and processing information to FE team 3 - Implement statistics model | 25
2 | 05/16 - 05/28 | 56 | 56 |  | 2 - Created the base Django and Front End code for the project which others developed on 3 - Implemented base models and survey model for Django 4 - Created tests for the Survey and question implementation 5 - Scheduled meetings and delegated tasks to team members and reached out to check progress 7 - Completing needed documents for iteration 1 |  | 30 | 8 | 3 | 2 | 10 |  | 3 | 2 - Created the base code in code as seen in commits 3 - Created base model placeholders as seen in commits 4 - Seen in my personal branch 5 - Seen through minutes and discord messages 7 Submission of iteration 1 | 1 - Not everyone is on the same page with development 2 - A member has left the team | 1 - Schedule more frequent meetings and check-ins 2 - Divide tasks amongst teammates | 1 - Create Data base 2 - Configure env for data base and testing | 60
3 | 05/16 - 05/28 | 0 | 0
4 | 05/28 - 06/11 | 0 | 0
5 | 06/11 - 06/18 | 0 | 0

## Jack Cairns
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 9.5 | 8.5 | 1 | 0 - review GitHub and its features, read through class documents about the project, read throug team coding standards 5 - minutes for first team meeting, informal meeting with team to ask questions to team leader 6 - set up GitHub access to repository key, joined team3, and debugged contributor errors | 3 |  |  |  |  | 2.5 | 3 | 0 |  | 1. I had an issue with GitHub not showing me as a contributor to my team's project 2. I had a late start to the course due to Spring courses | 1. Needed to add my BU email address to my GitHib account and have that match the email set in my local git config 2. Increase my time committmet and overall contributions in interations going forward | 0 - learn & review Django, Pandas, and NumPy, learn about my role as requirment leader 1 - review team design and provide concrete requirements based on other teams' plans 3 - implement a basic hello world on Django 5 - participate more in team activities 6 - setup PyCharm and Docker for local development environment | 6
2 | 05/16 - 05/28 | 5.5 | 5.5 |  | 0 - reviewing django class documentation 3 - implementation for question, choice, and response models 5 - minutes for meeting on 5/20 | 2 |  |  | 3 |  | 0.5
3 | 05/16 - 05/28 | 0 | 0
4 | 05/28 - 06/11 | 0 | 0
5 | 06/11 - 06/18 | 0 | 0

## Xi Zeng
Your Lead Roles: QA Leader / Design and Implementation Leader (DBs)
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 8 | 7 | 1 | 0 - learning git for team collaborate enviroment, django framework, revewing DBs, also learning from our course module 1 1 - Deside to use pandaSQL and django's build-in testing 5 - Understanding our specific micro-service needs from ZOOM Q&A, communicate in first team meeting | 5 | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  | Not farmiliar with pandaSQL, django's build-in testing, and git for team collaborate enviroment | Learning pandaSQL, django's build-in testing, and git for team collaborate enviroment from online enviroment | Building first draft ERD for DBs, Thinking throgh testing case from DBs side and communicating with teamate for their aspect of testing case. | 10
2 | 05/16 - 05/28 | 0 | 0
3 | 05/16 - 05/28 | 0 | 0
4 | 05/28 - 06/11 | 0 | 0
5 | 06/11 - 06/18 | 0 | 0