## Sheet1
}
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2024-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | A person joins the team | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Quickly onboard new member | Does not apply as of now | Open
| Lack of motivation or responsibility | Team members lack motivation to complete tasks | 3 | 3 | 3 | 27 | Team leader and all members | 2024-06-01 | Have regular weekly check-ins and 1-on-1's if needed | Ongoing communication and check-ins | Open
Communication | duplicate work | Team members are duplicating work | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Use project management tools like GitHub KanBan or something else to avoid duplications along with regular meetings | No duplicated work detected | Open
| worked on wrong components | Team member worked on wrong component | 1 | 3 | 2 | 20 | Team leader | 2024-06-01 | Regular check-ins and meetings along with a project management tool to prevent that | No wrong work detected | Open
| useless work | Work done that isn't useful to the project | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review work in meetings to check for work relevance | Hasn't happened | Open
| inconsistent work | Work quality is inconsistent | 2 | 3 | 2 | 24 | Tem leader and all members | 2024-06-01 | Follow coding standards and guidelines to review work consistency | Ongoing | Open
Requirements | unclear requirements | Requirements are not clearly defined | 2 | 4 | 3 | 36 | Requirement Leader | 2024-06-01 | Regular meetings with stakeholders to clarify and refine requirements. | Ongoing requirement refinement | Open
| scope creep | Uncontrolled changes in project scope | 3 | 4 | 3 | 27 | Team leader | 2024-06-01 | Implement change control process to manage scope changes. | Scope changes under control | Open
| constant requirements changes | Frequent changes in requirements | 3 | 4 | 3 | 27 | Requirement Leader | 2024-06-01 | Regular communication with stakeholders and iterative development to manage changes. | Managed through iterative updates | Open
Management | improper task assignments | Tasks not assigned properly | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review and adjust task assignments based on team skills and project needs. | Tasks reviewed regularly | Open
| improper planning | Poor planning of project phases | 2 | 4 | 3 | 36 | Team leader | 2024-06-01 | Regular planning sessions and reviews to ensure proper project planning. | Planning sessions ongoing | Open
| lack of management skills | Team lacks management skills | 2 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide management training and support for the team leader. | Ongoing management training | Open
Technology competence | Not familiar with the framework used | Team not familiar with Django framework | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Django. | Training sessions scheduled | Open
| Not familiar with the programming language used | Team not familiar with Python | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Python. | Training sessions scheduled | Open
| Not familiar with unit testing | Team not familiar with unit testing | 3 | 3 | 3 | 27 | QA Leader | 2024-06-01 | Provide training on unit testing practices and tools. | Training sessions scheduled | Open
| Other technology incompetence | Team lacks other necessary technology skills | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Identify skill gaps and provide training and resources. | Ongoing skills assessment | Open
| Not familiar with Git | Team not familiar with Git for version control | 3 | 3 | 3 | 27 | Configuration Leader | 2024-06-01 | Provide Git training and best practices documentation. | Training sessions scheduled | Open
Design and implementation | Improper design | Design does not meet project requirements | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Regular design reviews and stakeholder feedback sessions. | Design reviews ongoing | Open
| improper technology stack | Technology stack not suitable for project | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Evaluate and select technology stack based on project needs and team expertise. | Technology stack evaluated | Open
| Messy code | Code is disorganized and difficult to maintain | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-06-01 | Establish and enforce coding standards and conduct regular code reviews. | Coding standards enforced | Open
Testing | Not enough testing | Insufficient test coverage | 3 | 4 | 3 | 36 | QA Leader | 2024-06-01 | Ensure comprehensive test coverage by setting up testing frameworks and writing necessary tests. | Testing in progress | Open
Integration and deployment | Not enough time for integration and deployment | Inadequate time allocated for integration and deployment | 3 | 4 | 4 | 48 | Team leader and Configuration Leader | 2024-06-01 | Allocate sufficient time for integration and deployment phases in the project plan. | Time allocated in project plan | Open

## Team_3
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
add new team members
Lack of motivation or responsibility
Communication | duplicate work
worked on wrong components
useless work
inconsistent work
Requirements | unclear requirements
scope creep
constant requirements changes
Management | improper task assignments
improper planning
lack of management skills
Technology competence | Not familiar with the framework used
Not familiar with the programming language used
Not familiar with unit testing
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design
improper technology stack
Messy code
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.