## Team_3
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2024-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | Someone dropped | Closed
| add new team members | A person joins the team | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Quickly onboard new member | No one else joined | Closed
| Lack of motivation or responsibility | Team members lack motivation to complete tasks | 3 | 3 | 3 | 27 | Team leader and all members | 2024-06-01 | Have regular weekly check-ins and 1-on-1's if needed | Everyone completed the project with a good attitude | Closed
Communication | duplicate work | Team members are duplicating work | 2 | 3 | 2 | 24 | Team leader and all members | 2024-06-01 | Use project management tools like GitHub KanBan or something else to avoid duplications along with regular meetings | Duplicated work was removed | Closed
| worked on wrong components | Team member worked on wrong component | 1 | 3 | 2 | 20 | Team leader | 2024-06-01 | Regular check-ins and meetings along with a project management tool to prevent that | This was corrected | Closed
| useless work | Work done that isn't useful to the project | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review work in meetings to check for work relevance | This was corrected | Closed
| inconsistent work | Work quality is inconsistent | 2 | 3 | 2 | 24 | Tem leader and all members | 2024-06-01 | Follow coding standards and guidelines to review work consistency | Assignments have been completed | Closed
Requirements | unclear requirements | Requirements are not clearly defined | 2 | 4 | 3 | 36 | Requirement Leader | 2024-06-01 | Regular meetings with stakeholders to clarify and refine requirements. | Requirements completed | Closed
| scope creep | Uncontrolled changes in project scope | 3 | 4 | 3 | 27 | Team leader | 2024-06-01 | Implement change control process to manage scope changes. | The project is over. | Closed
| constant requirements changes | Frequent changes in requirements | 3 | 4 | 3 | 27 | Requirement Leader | 2024-06-01 | Regular communication with stakeholders and iterative development to manage changes. | The project is over. | Closed
Management | improper task assignments | Tasks not assigned properly | 2 | 3 | 2 | 24 | Team leader | 2024-06-01 | Regularly review and adjust task assignments based on team skills and project needs. | The project is over. | Closed
| improper planning | Poor planning of project phases | 2 | 4 | 3 | 36 | Team leader | 2024-06-01 | Regular planning sessions and reviews to ensure proper project planning. | The project is over. | Closed
| lack of management skills | Team lacks management skills | 2 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide management training and support for the team leader. | The team has been managed and completed the project. | Closed
Technology competence | Not familiar with the framework used | Team not familiar with Django framework | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Django. | Everyone learned Django and React. | Closed
| Not familiar with the programming language used | Team not familiar with Python | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Provide training and resources for team members to learn Python. | Everyone learned Django and React. | Closed
| Not familiar with unit testing | Team not familiar with unit testing | 3 | 3 | 3 | 27 | QA Leader | 2024-06-01 | Provide training on unit testing practices and tools. | Everyone learned Django and Selenium for testing. | Closed
| Other technology incompetence | Team lacks other necessary technology skills | 3 | 3 | 3 | 27 | Team leader | 2024-06-01 | Identify skill gaps and provide training and resources. | Everyone learned Django and Selenium for testing. | Closed
| Not familiar with Git | Team not familiar with Git for version control | 3 | 3 | 3 | 27 | Configuration Leader | 2024-06-01 | Provide Git training and best practices documentation. | People learned Git and GitHub. | Closed
Design and implementation | Improper design | Design does not meet project requirements | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Regular design reviews and stakeholder feedback sessions. | Design fixed. | Closed
| improper technology stack | Technology stack not suitable for project | 2 | 4 | 3 | 36 | Design and Implementation Leader | 2024-06-01 | Evaluate and select technology stack based on project needs and team expertise. | Correct stack was used. | Closed
| Messy code | Code is disorganized and difficult to maintain | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-06-01 | Establish and enforce coding standards and conduct regular code reviews. | Code was refactored. | Closed
Testing | Not enough testing | Insufficient test coverage | 3 | 4 | 3 | 36 | QA Leader | 2024-06-01 | Ensure comprehensive test coverage by setting up testing frameworks and writing necessary tests. | Tests were administered. | Closed
Integration and deployment | Not enough time for integration and deployment | Inadequate time allocated for integration and deployment | 3 | 4 | 4 | 48 | Team leader and Configuration Leader | 2024-06-01 | Allocate sufficient time for integration and deployment phases in the project plan. | The project is finished. | Closed